## Slide 1
CASE STUDY
CO-PRODUCTION

## Slide 2: CONTEXT
The Council has been running an annual Ageing Well Festival since 2022, as part of the Ageing Well Strategy and to observe International Day of Older People.
The Festival is a free event for Newham residents aged 50+ to:
celebrate residents aged 50+;
provide information about activities and services available in the borough;
connect residents;
enable residents to shape the annual Strategy actions.
In 2022 the Festival was attended by around 140 residents, in 2023, by around 450. The intention was to double this for 2024. Feedback from the Ageing Well Resident Advisory Group was they wanted to be more involved in the planning of the Festival.

## Slide 3: STRENGTHS-BASED APPROACH
A Task and finish Group was established with 12 residents from the Ageing Well Resident Advisory Group, six representatives from the Community, Voluntary and Faith Sector, and colleagues from various Council Teams and NHS.
We had a budget of £1,500!
The Group were very proactive and came up with a number of ideas regarding possible venues, information stalls. activities, entertainment and food.
Together we:
increased the budget to £9,660 by applying for external funding and Social Value donations;
were offered Forest Gate Community School for free, as the venue;
agreed an effective communication / promotion programme;
worked with local supermarkets (Asda, Iceland, Morrison's and The Coop) who provided free food;
worked with local groups (who we shared the food with) to create an International Food Court at the Festival;
worked with a number of organisations who attended as information stalls, based on the resident requests;
run a number of taster activities, based on the resident requests;
had a number of volunteers from the Resident Advisory Group and Newham Volunteers attend on the day to help with logistics.

## Slide 4: OUTCOMES AND IMPACT
The Festival took place on the 5th October 2024 and attracted over 900 residents!
In the main, we received positive feedback from residents, for example, ‘I just wanted to congratulate you, the team you lead and volunteers who put the festival together. What a fantastic event! It far exceeded my expectations and I’m so grateful for the opportunity to have attend such a useful AND fun event. I picked up all sorts of useful information and thoroughly enjoyed the relaxing embroidery class. Well done!’
Residents who took part in the planning felt heard and their views valued.
One of the volunteers, who had only been in the UK for two months and doesn’t speak English fed back ‘Thank you very much, it was a very nice activity, and for me it was a phenomenal experience, I had a great time. This encourages me to continue participating in these activities. God bless you’.
The volunteer used Google Translator on his mobile to communicate with staff, other volunteers and residents. Despite the language barrier, he rose to the challenge - he staffed the lifts supporting residents and those with mobility needs ensuring everyone was able to get access to the relevant floors. He also helped tidy up the food court and even had time to get his flu jab 

## Slide 5: LESSONS LEARNT AND REFLECTIONS
The Festival is a useful tool to communicate with residents aged 50+ what is going on in the borough. Having residents sitting on the planning group is so important to ensure we better understand the accessibility and communication needs of the residents we are trying to reach, and what activities / information should be available to encourage them to attend.
From the residents insights, we have learnt that its important to use a range of engagement methodologies, tools and materials recommended by the residents to promote to as many residents as possible.
On reflection, we are probably not equipped to run an event of this size by ourselves, as there were things that we didn’t think about which were fed back by some residents and stakeholders (e.g. having seats and beverages for when residents arrived, having arrows to help residents navigate such a large building, placing information stalls at the front of the building so these are the first thing residents access, having activities closer together and not happening at the same time to support those who struggle to walk distances, etc).
For 2025, we have started work with NHS partners, residents and a cohort of voluntary organisations who are better equipped / have greater capacity and experience of running large events.