## Slide 1
CASE STUDY
CO-PRODUCTION

## Slide 2: Context
In July 2021, the Government published a National Strategy for Autistic Children, Young People and Adults - replacing the Think Autism Strategy for Adults. The strategy aims to:
improve understanding and acceptance of autism within society;
improve autistic children and young people’s access to education - and support positive transitions into adulthood;
support more autistic people into employment;
tackle health and care inequalities for autistic people;
build the right support in the community and support people in inpatient care; and
improve support within the criminal and youth justice systems.
In 2022, colleagues from the Council’s Adults and Health Directorate and Children and Young People’s Directorate, alongside those from the ICB, ELFT and Metropolitan Police started working together to co-design, with autistic residents and their families, a local Autism Action Plan advising how these national aims will be met locally; and how additional, Newham-specific issues will be addressed. The Action Plan was published in April 2023 and can be viewed here.

## Slide 3: Strengths-Based Approach
A governance structure was established offering resident representation on the Delivery Board and a new Autism Residents Advisory Group (ARAG) was created as the platform for engagement with residents.
To establish the ARAG an open invitation was sent to autistic Adult Social Care users, Providers, and existing resident and co-production groups; alongside posters and flyers in public spaces (e.g. Libraries). The criteria for membership: diagnosed autistic or on the waiting list for an assessment, living in Newham and aged 18+.
It was apparent from the first meeting that the ARAG engagement platform was not accessible to all autistic residents. As such, VoiceAbility was commissioned to carry out a targeted piece of work with those who were autistic with learning disabilities. Three separate sessions were run using different communication tools including drawings, photos, objects and playing games. There were 15-20 residents involved.
An autism situationally mute survey and focus group was held in November 2024 to identify what barriers there were to engagement. There were 34 respondents, findings from this work led to changes in the way the ARAG is run including active use of the chat function, use of an avatar and no requirement for use of the camera. Situational_Mutism_Survey_Summary.pptx
ARAG meetings are held quarterly, in light of the co-production work required to build the Action Plan in Year 1, six focus groups were offered for residents to participate in shaping the Action Plan.

## Slide 4: Strengths-Based Approach
The Delivery Board is co-chaired with an autistic resident (who holds the role for 12 months), with another autistic resident representative and Carer of autistic resident representative in attendance.
The ARAG is also co-chaired with an autistic resident (who holds the role for 12 months).
To further engagement with residents in Year 2, six residents were appointed as local experts, one for each of the six working groups, reflecting the priority areas in the Action Plan. They would also be delivering on some of the actions that require co-production.
A total of nine resident experts have been appointed to continue to shape the Action Plan and support in the delivery of the actions. All resident experts are paid for their time.
All experts were supported with an initial group meeting to outline expectations with the Autism Lead and ongoing one-to-one meetings as required to support them and provide guidance and direction in their role/s. Experts will also be receiving support and guidance from the Working Group Lead.
At the soft launch of the Action Plan in April 2024, to ensure the event was accessible to autistic residents, coloured communication name badges were offered alongside a quiet room, floor plan, location map and direction details, agenda, individual speaker and stall details, numbered stalls with booking forms, goodie bag with an enclosed fidget toy amongst other items; and silent clapping.

## Slide 5: Strengths-Based Approach
Autism Resident Newsletters were produced in Year 2, in recognition of the reduced number of meetings from the first year, moving to monthly from October. This allowed residents to keep in touch and informed. The newsletter was extended to all residents who have been diagnosed or on the waiting list on the Newham Diagnostic Service and other parties. Support and Information for Autistic Residents
A WhatsApp group was also created in Year 2 in recognition that different people like using different platforms of communication.
At the ARAG in January 2025 we introduced the new inclusive communication style (situation speaking survey actions), combined with extending the newsletter to the autism diagnosis group, it was the highest number of attendees, with new participants who previously had no engagement.
A Newham Hospital World Café Autism staff and resident event was established to identify improvements that could be made in the hospital. A report was produced with recommendations for action. World Cafe: Autism
An autism champions group was soft launched in December 2024, to identify autistic people who want to engage but don’t know how and in recognition that local residents are keen to get involved to support autistic residents in the community – as evidenced from the volunteers who supported the launch in April.
A Newham Buddy Project Pilot was set up in January 2025 by the Volunteer Team Manager as a response to the several requests by autistic residents asking for an escort to meetings or appointments due to their anxieties – a common trait for an autistic person. An early test for the project was trialled by an autistic person and results were extremely positive.

## Slide 6: Strengths-Based Approach
In recognition of anxieties that lead to isolation, loneliness and depression in autistic people as well as eating disorders, the “Healthy Cooking” community project was approached to deliver a 4-week course of free cooking classes for autistic residents. This was received positively by the autistic community with high attendance numbers and led to volunteers offering to put on further activities.
The World Autism Awareness Week 2025 programme has introduced, for the first time, a large number of autistic residents volunteering activities including Remembering self-care during times of burn-out: Autistic Womens Craft Session., IT, Art & Music
A mini-health event was arranged for 1 hour after the ARAG meeting, autistic residents have one of the highest incidence of health inequalities. Residents were able to access health services including health checks, bowl and breast cancer. After the mini-health event, eight members stayed back for a further 1.5-2hours which formed a natural peer support group. The DB Co-chair volunteered to continue these quarterly informal peer support groups after each ARAG meeting.
The peer support strategy is built on enabling the local autistic community to make connections, build a network and form friendships in a safe space and respond to the needs of the community. The autism champions, volunteers offering activities and the resident experts form part of this strategy.
The same approach that was used to build resident trust was used with partner/stakeholder engagement. Building a safe supportive environment to allow partners to be heard and listened to with the autonomy to take forward the priorities in the Strategy. This enabled a strong senior representation at the DB and identification of working group leads across partner organisations including ICB, ELFT, Met Police, Fire Brigade.

## Slide 7: Strengths-Based Approach
Recognising our own autistic staff and their needs to enable them to remain in paid employment is also important: 29% of autistic people are in paid employment. A work related anxiety peer group was established in February 2025 as a need to support a staff member with their personal mental health; 10 participants signed up to the first meeting. A Council staff autism peer support group is also in the process of being set up.
An autism video was produced to bust the myths around employing autistic people and the simple minor adjustments needed to enable an autistic person to remain in employment https://youtu.be/19vkO10H0YY

## Slide 8: Outcomes and Impact
The Council has achieved a high level of engagement through:
  an open and transparent process;
  reflecting residents' conversation in the Action Plan;
  enabling residents' direct involvement in shaping and delivering the Action Plan;
  valuing residents' contributions through the Reward and Recognition Policy;
  having clear lines of communication.
  This has created trust, belonging and residents being valued and heard.
Identification of a lack of representation across the community engaging on the Strategy and stigma around autism in different cultures has led to work with the local faith leaders.
A lack of representation of men engaging in the Action Plan has instigated a future focus group launch during Autism Acceptance Week 2025 offering a platform for an autistic men only focus session to identify and understand their needs.
In recognition of the link between autism and suicide, a training pilot between Papyrus, a national suicide prevention charity, the Council, NHS and partners including local business, residents and practitioners is being designed.
Surveys, focus groups and engagement sessions have been delivered to engage with groups that are often excluded (e.g. autistic residents with learning disabilities and situationally speaking).
Many autistic residents do not seek a diagnosis for a number of reasons, but self-identify as autistic. In recognition of this the ARAG no longer restricts membership to those who have been diagnosed or on the waiting list.

## Slide 9: Lessons Learnt and Reflections
Opportunities can naturally arise and a keen eye to spot these is required to maintain the momentum for any project (e.g. the informal peer support group that naturally formed after the January 2025 ARAG meeting was formalised as a regular group within the week).
Information and resources form an important part of the communication channel with residents and stakeholders in between meetings to maintain the engagement. It is important to offer both local and national newsworthy content and material that would reflect the various needs of the group.
Volunteers have been an incredible source of support, particularly so for the autism soft launch event.
Building trust in any community requires time and patience, building the momentum is key to this and creating a safe space for autistic residents and supporting their needs is fundamental.
Strong stakeholder relationships are key to delivering an integrated Action Plan.