## Slide 1
ADULT LEARNING DISABILITY ACTION PLAN
You Said, Together We Did
Year 2 Progress Report - August 2024

## Slide 2: Overview
This report captures the actions in the Adults Learning Disability Action Plan that were identified to be delivered in Year 2, along with those in the You Said, Together We Did Year 1 Progress Update.
The status of each action is recorded at the top of the page:
ØCLOSED - indicates the action has been completed and assumed, where appropriate, into ‘business as usual’ activity;
ØCOMPLETE - indicates the action has been completed, but has evolved to include new tasks;
ØIN PROGRESS - indicates the action has been started, but not completed;
ØNOT STARTED - indicates the action has not started due to employee capacity or resource;
ØREMOVED - indicates that the action has been removed following discussion with the action owner and Resident Advisor Group.
There are Dashboards at the end of each section to analyse data trends. Where there has been a minimal increase or decrease (i.e. 5% change or less) we will use amber arrows. e.g.
Action 3.1 - Develop existing community assets and resources to enable residents with Learning Disabilities the opportunity to access them – has been removed, as this has been addressed via Actions 4.4, 4.5 and 4.6.
There is a Jargon Buster at the end of this document to explain some of the words that we have used in this document.

## Slide 3
OUTCOME 1: HEARD AND VALUED

## Slide 4: ACTION 1.1 - Raise Awareness
Raise awareness of Learning Disabilities; and the impact on those who have them. Within this is the annual observation of: Learning Disabilities Week, Down Syndrome Day; and within other relevant annual observation events
Year 2 Update:
The Council co-designed a series of activities for Learning Disability Week 2023. There were multiple events and activities held ahead of the week, and during Learning Disability Week. There were 297 attendees over the week, including 28 at the Art Exhibition opening at Beckton Library, 99 at the Variety Show and 163 at the ‘Get Together’ BBQ,.
On the 21st March 2024, the Council held its second all-age observation of World Down Syndrome Day. This had presentations by four adult residents with Down Syndrome about their accomplishments and skills to children with Down Syndrome, their parents and professions.
There was also Learning Disability representation at the Carers Festival 2023 and the Aging Well Festival 2023.
CLOSED
Year 3 Tasks:
Continue as Business as Usual:
Co-design a series of activities for Learning Disability Week 2024 and World Down Syndrome Day 2025;
Explore with the Learning Disabilities Resident Advisory Group how the Council can further raise awareness of Learning Disabilities and the impact on those who have them within the general Newham population.

## Slide 5: ACTION 1.2 - Training
Develop and implement a Learning Disabilities awareness training programme for Council staff and its partner organisations
Year 2 Update:
The Council and its Health partners delivered the following training sessions / programmes:
The Council has a Making Research Count membership providing access to best practice initiatives for Health and Social Care professionals.
The Council has commissioned Grey Matter Learning training across Health and Social Care. This is free and accessible to all Newham Providers who have registered with Care Providers Voice, as well as Adult Social Care Staff.
COMPLETE
Year 3 Tasks:
Roll out Oliver McGowan Tier 1 and 2 Training to all relevant CQC registered providers.
Training Session / Programme | Attendees | Training Session / Programme | Attendees
i-Support: L3 (Carers) | 23 | *Offered by the Community Health Team to support individual residents. | 

## Slide 6: ACTION 1.4 - Resident Forums
Refresh the forums (including the Learning Disability Partnership Advisory Group [LDPAG]) for people with Learning Disabilities to enable regular feedback of views and experiences of Health and Social Care and wider issues that affect lives.
CLOSED
Year 2 Update:
The Learning Disability Resident Advisory Group. The Group meets quarterly face-to-face. It is an opportunity for residents to feed into the delivery of the Action Plan. The Resident Advisory Group is Co-chaired by a resident with a lived experience. To join the Group online click here. Or email: LearningDisability.Commissioning@newham.gov.uk. These meetings feed into the Action Plan Delivery Board.
The Learning Disabilities Action Plan Delivery Board also runs quarterly. The purpose of the Board is to realise the six Outcomes in the Action Plan. There are two residents with lived experience sharing the Co-chair role for the Delivery Board. These meetings feed into the Resident Advisory Groups and the Learning Disability and Autism Joint Planning Group.
East London Foundation Trust (ELFT) has a dedicated People Participation Lead in their Learning Disability Service who undertakes regular resident engagement sessions around Health needs. To join the sessions email: simon.bedeau@nhs.net.
Year 3 Tasks:
Continue as Business as Usual
Increase the number of residents signed up to the Learning Disability Resident Advisory Group and ELFT sessions.
Elect new Co-Chairs for the Resident Advisory Group and the Action Plan Delivery Board.

## Slide 7: ACTION 1.5 - Advocacy Service
Review the Integrated Advocacy Service in relation to its effectiveness for people with Learning Disabilities.
CLOSED
Year 2 Update:
The Council has a Contract with VoiceAbility for the provision of an Advocacy Service. The Council is currently re-procuring it’s Advocacy Contract. Changes have been made to the new contract to improve access to Independent Mental Capacity Advocacy for residents placed in accommodation outside of Newham.
Monthly Learning Disability self-advocacy drop-in sessions began from the 9th October 2023 at Chargeable Lane Resource Centre. These now run monthly on the second Monday of the month. The Learning Disability drop-in runs from 1-2pm, there is a session from 2-3 where those with learning disabilities and/or autism can attend.
To find out more or access the Service visit: VoiceAbility Newham or ring: 0300 303 1660.
Year 3 Tasks:
Continue to monitor reach and usage of the Advocacy Service via the protected characteristics of those residents using the Service.
The Advocacy Service Contract expires on the 31st August 2024. This is currently being retendered. The new contract has additional employment and training supports for residents with disabilities and Carers as part of the Social Value element of the contract.
Continue to build on Self-Advocacy and Peer Advocacy in Newham, to develop skills and confidence.

## Slide 8: DASHBOARD - Heard and Valued
‘I’ STATEMENT | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
I can access information and advice when I need it to help me understand my options and make informed decisions. | % of residents who use services who find it easy to find information about support. Source: Adult Social Care Survey | 45% | 92% | 69.7% |  | 
I am helped to make my voice heard about things that affect my life. | No. of residents signed up to the Learning Disabilities Resident Advisory Group. Source: Resident Advisory Group Database | - | 11 | 19 |  | 
 | No. of residents signed up to the ELFT People Participation Group. Source: ELFT People Participation Database | - | 15 | Not available |  | -
 | No. of residents accessing the Newham Advocacy Service (with a Learning Disability identified). Source: Provider Contract Returns | 94 Users | 92 Users | 110 Users |  | 

## Slide 9
OUTCOME 2: ACCOMMODATION AND HOUSING

## Slide 10: ACTION 2.1 - General Housing Tenancies
Review support available for residents with Learning Disabilities to maintain tenancies in general housing.
Year 2 Update:
Best Practice and Guidance information on supporting people with Learning Disabilities in General Housing and Easy Read support documents shared with Housing Services and Temporary Accommodation Services. This will need to be finished in Year 3.
Newham’s Planning Department commissioned research into Housing Design. They consulted with the Learning Disability Resident Advisory Group, the Learning Disability and Autism Provider Forum, and held two workshops with residents with Learning Disabilities and/or Neurodivergent needs. The outcomes of the research will inform the implementation of the new Local Plan policies.
Year 3 Tasks:
Work with Newham Living and Housing partners to develop support options.
Complete work on Best Practice Guidance information on supporting people with Learning Disabilities in General Housing (see above).
Newham’s Local Plan is currently open for consultation. Please see the website for updates.
IN PROGRESS

## Slide 11: ACTION 2.3 – Shared Lives
The Council will review the Shared Lives offer
Year 2 Update:
A Review of Shared Lives was completed in year 2.
Year 3 Tasks:
Implement recommendations from the Shared Lives Review
1-2 Residents who live in Shared Lives accommodation to be supported to join the Resident Advisory Group
COMPLETE

## Slide 12: ACTION 2.2 Floating Support
The Council will look at how it buys housing support / floating support services.
Year 2 Update:
A review of how the Council buys how it buys housing support/ floating support services for residents with mental health conditions.
Year 3 Tasks:
Once the Mental Health review is completed, a review for Learning Disability support will begin.
NOT STARTED

## Slide 13: ACTION 2.4 - Care Homes
Care Homes - Complete a Needs, Capacity and Opportunities Assessment.
CLOSED
Needs, Capacity and Opportunities Assessment completed and Action Plan implemented to address the issues and opportunities identified.
Market Position Statements for Older Adults (65+) Care Homes developed and agreed. These can be viewed at: www.newham.gov.uk/health-adult-social-care/market-position-statements/1

## Slide 14: ACTIONS 2.5 and 2.7 - New Housing
Exploring new developments to increase availability of options for in borough accommodation for people with Learning Disabilities.
IN PROGRESS
Year 3 Tasks:
Complete redesign and/or procurement of specialist Learning Disability Supported Living provisions, including:
  Ranelagh Road
  Chants Square
Year 2 Update:
Call-off Supported Living schemes for specific need-groups as identified in the Needs, Capacity and Opportunities Assessment, as part of the Council’s Supported Living Transformation Programme.
The Council has a number of Learning Disability specific Supported Accommodations that are being re-designed or re-procured under the Dynamic Support Vehicle. These are to be completed in Year 3.

## Slide 15: DASHBOARD - Accommodation and Housing
‘I’ STATEMENT | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
I have a place to live of my choosing | % of residents with a Learning Disability in receipt of Long Term Services who live in their own home or with family. *Target 80%. Source: AzeusCare | 83% | 87% | 86% | - | 
 | % of residents with a Learning Disability who live in an in-borough Supported Living scheme. Source: AzeusCare | 82% (132 / 161) | 85% (129 / 152) | 80% (134 /168) | - | 
 | % of residents with a Learning Disability who live in an in-borough Care Home. Source: AzeusCare | 30% (33 / 111) | 26% (24 / 91) | 28% (23 / 83) | - | 
 | % of residents with a Learning Disability who advised their home is designed to meet their needs. Source: Adult Social Care Survey (Learning Disability) | 77% | 92% | 82% | - | 
 | % of residents with a Learning Disability who would describe their home as clean and comfortable. Source: Adult Social Care Survey (Learning Disability) |  | 99% | 71% | - | 

## Slide 16
OUTCOME 3: CONNECTED AND INVOLVED

## Slide 17: ACTION 3.2 - Support Worker
There is short-term Health Funding the employment of an additional Support Worker to specifically support residents with Autism and / or Learning Disabilities - with the aim of reducing social isolation and loneliness.
;
REMOVED
Year 2 Update:
This project shifted in focus in Year 1 to meet Operational demands in Adult Social Care – with the Support Worker supporting Autistic residents, though some also have Learning Disabilities.
Year 3 Tasks:
This funding ended in Year 2.

## Slide 18: ACTION 3.4 – Assistive Technology
Improve awareness of and access to Assistive Technology and Community Equipment.
;
Year 3 Tasks:
Newham Council to explore Assistive Technology offer and how this is embedded into Independent Living Support Services and Enablement offers.
IN PROGRESS

## Slide 19: ACTION 3.5 Non-Exploitation Policy
Write a Learning Disabilities Non-Exploitation Policy
;
CLOSED
Year 2 Update:
In October 2022, the Council published a Hate Crime Strategy. This Strategy addresses a number of issues raised by residents aged 50+.
Training started in February and to date 60 frontline staff members have been trained.
A new Hate Crime reporting service has been established. To report a hate crime visit: stophateuk.org/report-hate-crime0 or call 0800 138 1625 (24hrs a day).
Year 3 Tasks:
Closed

## Slide 20: ACTION 3.6 and 3.7 - Sex and Relationships
Co-design and implement a Relationships Policy and guidance including training programme for residents with Learning Disabilities.
;
IN PROGRESS
Year 2 Update:
A Sex and Relationships Charter and Sex and Relationships Policy for in-borough accommodation-based Providers has been drafted.
This has been circulated to internally for input from the Operation’s Learning Disability Teams and the Neighbourhood Teams as well externally from three Care Homes and Care Providers Voice.
Further input to be sought from NEL ICB, Care England and other Local Partners, with amendments made accordingly.
Year 3 Tasks:
Sex and Relationships Charter and Sex and Relationships Policy for in-borough accommodation-based Providers to be presented to accommodation-based Providers and the Resident Advisory Group for comment; and once agreed launched.
Sex and Relationship Charter and Sex and Relationships Policy to be finalised.

## Slide 21: DASHBOARD - Connected and Involved
‘I’ STATEMENT | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
I am free from abuse, harm and discrimination. | Safeguarding raised for adults with Learning Disabilities: No. of Concerns No. of S42 Enquiries Risk Reduced or Removed Source: AzeusCare and PowerBI | - | 96 54 83% | 79 53 80% |  | 
I am accepted by my local community regardless of who I am, where I live or the circumstances of my life. | % of residents with a Learning Disability who advise they are able to get around their community. Source: Adult Social Care Survey (Learning Disability) | 37% | 70% | 42% |  | 
I have a range of supportive relationships of my choosing. | % of residents with a Learning Disability who advise they have as much social contact as they would like. Source: Adult Social Care Survey (Learning Disability) | 93% | 89% | 88% |  | 

## Slide 22
OUTCOME 4: WORK AND PURPOSE

## Slide 23: ACTION 4.1 - Pathways
Review pathway from education to further education for residents with Learning Disabilities - to identify and address the areas for improvement.
COMPLETE
Year 2 Update:
Our Newham Learning and Skills
227 learners have attended SEND classes over the last academic year 2023/24.
This links into activities described in Outcome 2.
Year 3 Tasks:
Review the pathway to employment.

## Slide 24: ACTION 4.2 - Social Value
Explore use of Social Value to encourage employment opportunities for residents with Learning Disabilities.
IN PROGRESS
Year 2 Update:
The Council has been working with Housing Development Providers in order to target additional support for residents accessing Adult Social Care Services and specific groups, including residents with Learning Disabilities.
The Council’s Adults, Health and Communities Commissioning Team uses CommuniTeas and Coffees (a Learning Disability Social Enterprise) for meetings, as and when required.
Year 3 Tasks:
Monitor the number of employment opportunities for resident with Learning Disabilities provided and taken up via Council’s contracts.
Additional training and volunteering options for residents with Learning Disabilities (and their Carers) will be provided in Year 3, as part of the new Advocacy Contract.

## Slide 25: ACTION 4.3 - Supported Employment
Refresh the Supported Employment offer - with a view to expand it and increase the number and variety of employment opportunities.
Year 2 Update:
In Summer 2023, one new resident was trained to take part on the East London Foundation Trust interview panels.
A dedicated Commissioning lead on Supported Employment is in post.
Year 3 Tasks:
Supported employment opportunities for Residents with Learning Disabilities (and autism) are being explored as part of the roll out of the Oliver McGowan Mandatory Training.
Newham are reviewing the in-house provision with the aim of developing a better pathway to employment for those who are Care Act eligible.
IN PROGRESS

## Slide 26: ACTION 4.4 - Day Opportunities
Refresh the current Day Opportunities offer to make it more community-focused with both recreational activities and employment opportunities (for working-age residents).
IN PROGRESS
Year 2 Update:
The Council has worked with the London Boroughs of Havering, Redbridge and Waltham Forest to develop Minimum Quality Standards for Adult Day Opportunities. Once agreed, these will be used in conjunction with local Quality Assurance processes to improve Day Opportunities.
Newham’s In-House PMLD (Profound and Moderate Learning Disability) Day Opportunity moved from Mariner Road to Chargeable Lane.
A number of new initiatives were launched in year 2 as part of the Loneliness Action Plan, including Chatty Cafes, Men in Sheds and Talking Benches.
Year 3 Tasks:
The Council’s Community Opportunities Team is being restructured. They will be focussed on creating more employment opportunities.

## Slide 27: DASHBOARD - Work and Purpose
‘I’ STATEMENT | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
I am supported to develop and learn. | Students with Learning Disabilities attending Our Newham Learning and Skills. Source: Our Newham Learning and Skills | 192 | 178 | 227 |  | 
I have opportunities to engage in meaningful activities, including employment. | % of working-age adults with Learning Disabilities supported in paid employment. Source: ASCOF | 8.9% | 3.2% | 2.8% |  | 
 | % of people with Learning Disabilities in employment who are Care Act Eligible *Target is 3%. Source: Adult Social Care and Health Power BI | 3.3% | 2.9% | 1.3% |  | 
 | Number of residents with Learning Disabilities receiving support from the Enterprise Scheme. Source: AzeusCare | - | 15 | 15 |  | -
 | Number of residents with Learning Disabilities receiving support from Our Newham Works Supported Employment Team Source: AzeusCare | 22 | 42 | 61 |  | 

## Slide 28
OUTCOME 5: HEALTH AND SOCIAL CARE

## Slide 29: ACTION 5.1 - Improve Recording
Improve the recording on the Council’s Learning Disability Adult Social Care Database and Primary Care Learning Disability Register.
IN PROGRESS
Year 2 Update:
There was a focus on improving data to ensure all residents with a Learning Disability are recorded as such on Azeus Care, the Council’s Social Care database. Social Care Practitioners to ensure that Azeus Care records hold all the protected characteristics of those with a Learning Disability to better understand intersectional inequality.
Newham’s Health Peripatetic Nurses are working with GP surgeries to ensure all residents (aged 14+) with a Learning Disability have the correct diagnosis recorded on Health databases.
There is work being done across Health and Social Care (Children’s and Adults) in order to agree to address variations in terminology and usage across services in order to improve shared understanding and data collection.
An Adults Power BI dashboard has been set up that can disaggregate for Learning Disabilities / those open to the Adults 18-24 and 25+ Learning Disabilities Teams. This has supported an increased use of data to inform trends and gaps.
Year 3 Tasks:
Build on improved data collection across Health and Social Care.

## Slide 30: ACTION 5.2 – Develop an Adult Diagnostic Service
5.2 Develop and implement a Learning Disability Diagnostic Service (taking account of the diagnostic pathway for children and young people).
CLOSED
Year 2 Update:
The Learning Disability Action Plan had this as a Year 2 Action to develop and implement a Learning Disability Diagnostic pathway /service.
Due to the shortage of funding options available we have not been able to progress this action in year 2 delivery.

## Slide 31: ACTION 5.3 - Equal Health Access
Ensure parity of Health access and treatment for those with a Learning Disability.
IN PROGRESS
Year 2 Update:
A scoping exercise to map the Mild to Moderate Health Offer in Newham against the Offer across the North East London footprint has been completed.
From April 2023, the Community Health Team for Adults with Learning Disabilities transferred to the Adult Mental Health Directorate.
The Council’s Public Health Team are developing a Healthy Weight offer for residents with Learning Disabilities. They have developed this following consultation with residents. The project group involves NEL ICB and ELFT partners.
NUH will be aiming to reduce waiting times for patients with Learning Disabilities for elective care to at least the mean waiting time, and hopefully to less than this.
ELFT commissioned a Health Needs Assessment which was finalised in April 2024. Link Learning Disabilities in Tower Hamlets, Newham and City and Hackney Health Needs assessment report.
50 Steps for a Healthy Newham 2024-29. This now contains a specific step regarding Equity – Step 19 Make Newham a neurodiversity- and disability-friendly borough.
Year 3 Tasks:
Newham Public Health Team to procure a Learning Disability specific Healthy Weight Project.
Work across Health and Social Care to identify how to address recommendations in the ELFT Health Needs Assessment.

## Slide 32: ACTION 5.5 - Annual Vaccination
Support people with Learning Disabilities with annual vaccination programmes such as flu and Covid-19.
COMPLETE
 | Flu (data to 02.2022 - 02.2023) |  |  |  |  |  | Covid-19 |  | 
 | Given | Given by other providers | Total Uptake | Declined/ contrary indicated/ allergies/ no consent | Not contacted / Approached | Total Not Given | Given | Not Given | Uptake
Primary Course | 747 | 182 | 929 (49%) | 520 | 445 | 965 (51%) | 1,266 | 328 | 79.4%
Autumn 2023 Booster | 752 | 182 | 934 (47%) | 681 | 398 | 882 | 644 | 929 | 52%
Year 3 Tasks:
Promote reasonable adjustments and accessible information to increase understanding of the benefits of the vaccination programme in order to increase uptake.

## Slide 33: ACTION 5.6 - Reduce Admissions
Reduce inpatient beds in line with NHSE* Learning Disability and Autism Programme* targets and reduce the length of time that people stay in an inpatient setting.
.
COMPLETE
Year 2 Update:
This has been added as priority for the Learning Disability and Autism Joint Planning Group. The Integrated Care Board has commissioned a Learning Disability Nurse to provide oversight – with Learning Disability Nurses attending Ward Rounds and Care and Treatment Reviews for patients who have a Learning Disability.
The Dynamic Support Register has been reconfigured in line with NHSE national recommendations.
Safe and Wellbeing Reviews were completed for all hospital admissions in 2022/23.
Year 3 Tasks:
An inner North East London Intensive Support Team was established in July 2024 for Newham, Tower Hamlets, and City and Hackney to look at reducing hospital admissions and Provider / family breakdown. The Team will go live in September 2024.
Work will be done in partnership with the Newham Centre for Mental Health (NCfMH) to review the environment and interventions offered to patients who have Learning Disabilities. The Newham Health Team for Adults with Learning Disabilities attend all LD related ward rounds and CTR's. An ongoing, learning disabilities training programme for clinical staff is in place and plans are in progress to expand this in 2024/25

## Slide 34: ACTION 5.7 - Strengthen C(E)TRs
Continue to embed and strengthen Care (Education) and Treatment Reviews [C(E)TR] awareness and training, in partnership with stakeholders to assess their effectiveness in preventing and supporting discharge planning.
.
COMPLETE
Year 2 Update:
There is a new and C(E)TR process in place that includes more patient-focussed outcomes
C(E)TR specific training for some partners take place in 2023/24, provided by the North East London Integrated Care Board.
Year 3 Tasks:
Continue as Business as Usual.
C(E)TR’s Completed July 2023 to June 2024
Adults – 12 delivered (+ 5 refused consent)
CYP – 6
*Note a Care Education and Treatment Review is held for residents under 25 who have education needs. All others will be offered a Care and Treatment Review.

## Slide 35: ACTION 5.9 - Improve the Transition Offer
Improve the offer for transition-aged residents (14 - 25). Including the implementation of recommendations from the SEND Transformation Review.
COMPLETE
Year 2 Update
Post-16 Commissioning work will continue with Children’s and Adult’s Commissioners regarding the offer for residents in this group.
A Transition Panel has been established between SEND and Adult Operations, in order to improve pathways.
Transition-aged young people have been included in the Down Syndrome Day Celebration. The celebration focussed on adults telling young people and their families about their successes in adulthood in order to raise aspirations.
A member of CAMHS (Child and Adolescent Mental Health Services) is now spending a day a week with the Newham Health Team for Adults with Learning Disabilities to identify and take forward shared clinical development opportunities.
Year 3 Tasks:
There will be a Transition to Adulthood themed Local Offer Live in October 2024.
Young people were included in the Learning Disabilities Week Celebration BBQ at Chargeable Lane.
Newham are developing a transition dashboard. We will be actively looking at those who will need supported accommodation - agreeing a fit for purpose offer allowing for a smooth transition;
Newham will be procuring an all-age ILSS framework (go live July 25) - to both allow consistency from child to adulthood and to embed more of a provider led strength based approach

## Slide 36: ACTION 5.10 – Substance Misuse
Improve the offer for people with a Learning Disability who experience substance misuse issues.
Year 2 Update:
A new lead Commissioner has been appointed to lead on Substance Misuse.
Work with Change Grow Live (CGL) / Rise Newham regarding data collection.
Improve access pathways for individuals with dual diagnoses (Learning Disability and Substance Misuse) to both Substance Misuse Services and Adult Social Care.
Health and Social Care Commissioning Leads for Learning Disabilities have met with CGL, they are working on improving pathways for our residents who have additional needs related to substance misuse.
Year 3 Tasks:
Continue to work with Change Grow Live (CGL) / Rise Newham to improve the offer and uptake of substance misuse support.
IN PROGRESS

## Slide 37: ACTION 5.11 – Improve the Social Work Offer
Improve the Social Work offer via the Learning Disabilities Teams.
IN PROGRESS
Year 2 Update:
The Council is continuing to work toward ensuring sufficient Social Work capacity. This has been difficult due to a national Social Worker recruitment crisis.
Autism has been separated from the Learning Disability Teams in order to target resources and specialise expertise.
Year 3 Tasks:
The Council will develop a Learning Disabilities (and Autism) Induction Pack for Social Workers. This will include working with residents to develop videos / training to support induction.

## Slide 38: ACTION 5.12 - Support for Parents who have Learning Disabilities
Review the pathway / support for parents with Learning Disabilities.
Year 2 Update:
Support currently falls under universal services, though parents and parents to be who have Learning Disabilities is eligible for additional support via the Learning Disability Hospital Liaison Nurses, Adult Social Care and Health Community Team for Adults with Learning Disabilities.
Year 3 Tasks:
A Task and Finish Group to explore further developments in this area will be established.
IN PROGRESS

## Slide 39: ACTION 5.13 - Access for Older People
Review access for Adults with Learning Disabilities to Older Adults Services.
IN PROGRESS
Year 2 Update:
The Community Health Team for Adults with Learning Disabilities has an early-onset Dementia provision for residents with Down Syndrome.
The Dementia Pathway will be reviewed against the NICE guidelines.
The Aging Well Festival 23/24 included a table for aging well with a Learning Disability.
Year 3 Tasks:
Commissioning to Organise an Aging Well themed meeting for the Learning Disability and Autism Provider Forum in January 2025.

## Slide 40: ACTION 5.14 Review Joint Funding Arrangements
Review joint funding arrangements between Health and Social Care. Including review of Continuing Health Care budgets and the Joint Funding arrangements.
NOT STARTED
Year 2 Update:
Not started
Year 3 Tasks:
Re-establish conversations, including appropriate tool and agreements for Continuing Health Care, Joint-Funding and Section 117.

## Slide 41: ACTION 5.15 - Map Commissioned Services
Map commissioned services / Providers used by Children and Young People’s Services and Adults Services.
Year 2 Update:
Newham Family Information Service and our Local Offer for children and young people with Special Educational Needs and Disability (SEND) and their families can be found on Newham Families Advice and Support. This is updated on a regular basis.
For Adults, the Newham Health and Care Partnership developed Well Newham which brings together a range of health and well-being services. These can be accessed through the Well Newham Hubs and online on Helping everyone in Newham to live well | Well Newham
The Council has commissioned services from the Joy Platform in order to support resident access. For more information see: Joy | Social Prescribing Software (thejoyapp.com)
Year 3 Tasks:
Continue to work with Providers and residents with Learning Disabilities to ensure the above platforms are accessible; and evaluate use by residents with Learning Disabilities.
Continue to promote the role of Social Prescribers and Community Neighbourhood Link Workers in supporting residents face to face in order to access the platforms above.
IN PROGRESS

## Slide 42: ACTION 5.19 – Personal Health Budgets
Look at how Personal Health Budgets are provided in Newham.
Year 2 Update:
Aim to increase the number of Personal Health Budgets for those who are eligible.
Year 3 Tasks:
IN PROGRESS

## Slide 43: ACTION 5.20 - PBS Training
Procure and implement Positive Behaviour Support Training for Health and Social Care professionals and Carers to improve the quality of support and interventions for people who exhibit behaviours that challenge
CLOSED
Year 2 Update:
The Community Health Team for Adults with Learning Disabilities provide person-specific support to Carers and Providers.
I-Support Behaviour provided PBS Support Training for Carers in Year 2.
The Supported Living Dynamic Purchasing Vehicle includes the requirement for Learning Disability Providers to be Positive Behaviour Support trained.
Year 3 Tasks:
I-Support Behaviour will provide a deep dive into the effectiveness of the PBS Training for Carers, front-line staff, managers and those who wish to coach staff in PBS techniques/interventions.

## Slide 44: ACTION 5.21 - Community Nursing
Promote the support provided by the Peripatetic Nurses to commissioned services and residents with Learning Disabilities and their families living in the community
COMPLETE
Year 2 Update:
The Learning Disabilities assessment pathways for breast and bowel cancer screening were developed and implemented.
It was envisaged that PCLN's would not hold a clinical caseload; however, this has not been possible due to known gaps in service provision for residents with Mild to Moderate Learning Disabilities.
Promote the new 14-25 Hospital Passports - to strengthen links between Children’s and Adults with a focus on transition.
Year 3 Tasks:
There is an NHS requirement to increase uptake of Cancer Screening for residents.

## Slide 45: ACTION 5.22 – Increased understanding of Epilepsy, Mental Health and Suicide
Increase understanding and plans about Epilepsy, Mental Health and Suicide.
IN PROGRESS
Year 2 Update:
Increased of understanding of the benefits of Cancer screening were added in Year 2.
The Newham Health Team for Adults with Learning Disabilities have been working closely with the North London and Central and East London Breast Screening Service to support all women aged 50+ to attend their breast screening appointment. Where this is not possible, breast check awareness information shared with parents/carers. The effectiveness of this piece of work is being captured in a Quality Improvement Project.
Bowel Cancer Screening project to start in late 2024.
Year 3 Tasks:
Work to continue from Year 2.

## Slide 46: ACTION 5.23 Bereavement Service
5.23 Review the Community Bereavement Service’s specialist support for people with learning disabilities
CLOSED
Year 2 Update:
This offer was reviewed in Year 2, and funding was stopped.
Year 3 Tasks:
This service was decommissioned in Year 2.
Residents can continue to access Bereavement support from Newham Talking Therapies or the Community Team for Adults with Learning Disabilities (if they cannot access Talking Therapies).

## Slide 47: ACTION 5.24 End of Life Planning
Improved End of Life planning
Year 2 Update:
Improve End or Life planning awareness
Increase use of Advanced Planning documents
St Joseph’s Hospice have developed a number of Easy Read Resources around Palliative Care. They can be found here.
Year 3 Tasks:
Commissioning will host an Aging Well themed meeting for the Learning Disability and Autism Provider Forum in January 2025. This will include presentations from Palliative Care Services (NHS and St. Joseph’s Hospice).
IN PROGRESS

## Slide 48: ACTION 5.25 - LeDeR
Review the requirements of the Learning Disabilities Mortality Review Programme (LeDeR*) alongside existing End of Life Care pathways for adults with Learning Disabilities.
COMPLETE
Year 2 Update:
Common themes found in reviews completed between April 2022 to March 2023 LeDeR Report include:
Recognising deterioration and making referrals in a timely manner (Significant 7+);
Absence of individual discussions about Advanced Care Planning and lack of confidence amongst staff to have these discussions;
Absence of Independent Mental Capacity Advocates for those who may lack capacity to support these discussions;
last minute referrals (during last hospital admission) and in some cases the resident dying before the referrals have been actioned.
A group has now been set up with ASC and Health to discuss the learning from LeDeR to try and avoid similar issues arising for other Newham residents
Year 3 Tasks:
Staff training on recognising deterioration (this is already happening in BHR [Barking, Havering and Redbridge] - who work closely with Palliative Teams);
Empower staff to have Advanced Planning conversations with – providing material in accessible formats and enabling choice.
Promote the Advocacy Service to support staff with these discussions;
Ensure clear documentation of individual wishes is in place where discussions do occur.

## Slide 49: ACTION 5.26 - STOMP / STAMP
Link in with national STOMP* and STAMP* programme to prevent over-medication of residents with Learning Disabilities
Year 2 Update:
Since implementing STOMP and STAMP, the number of STOMP patients has reduced from 153 to 80. Of the 80, 44 (55%) are on a STOMP medication reduction plan - and the other 45% are regularly reviewed with a plan to reduce in the future. Nine patients have completely stopped antipsychotics.
GP training sessions to be arranged to raise awareness of STOMP*, STAMP*; and the importance of psychotropic medication reviews for residents with challenging behaviours;
Roll-out the NELFT piloted STOMP*-inclusive Structured Medication Review template across North East London.
Continue work between the ELFT Adults Pharmacist and the ELFT CAMHs Pharmacist.
*See Jargon Buster at the end of this document for more information about STOMP and STAMP
Year 3 Tasks:
To continue as Business as Usual.
CLOSED

## Slide 50: Health and Social Care Dashboard
OUTCOME | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
Improve Recording | No. of residents on the Primary Care Learning Disability Register Source: NHS Data | 1742 | 1635* | 1681 |  | 
Equal Access to Health Services | % of eligible adults with a Learning Disability having a GP Health Check. Source: NHS Data | 84% | 89.11% | 86% |  | 
Reduction in unplanned hospital admissions. | No. of residents with a Learning Disability in an inpatient setting. Source: Newham ICB data | 8 | 3 | 5 |  | 
 | No. of residents with a Learning Disability on the Dynamic Support Register** Source: Newham ICB data | 31 | 19 + 1 with LD query | 19 (red, Amber, Blue, Purple, no Green included) |  | 
*Decrease may be due to improved data recording in place. ** See Jargon Buster fro more information on the Dynamic Support Register

## Slide 51: Health and Social Care Dashboard
OUTCOME | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
Control over daily life | % of people who feel they have control over their daily life (%) Source: Adult Social Care Survey (Learning Disability) | 85.7% | 88% | 85.5% |  | 
Bereavement Service | No. of residents with a Learning Disability accessing the Community Bereavement Service. Source: Mind in Tower Hamlets and Newham | 26 | 24 |  | This service has been de-commissioned. | 
Positive Experience of Care and Support Services | Do care and support services help you to have a better life? Source: Adult Social Care Survey (Learning Disability) | 94.4% | Not available | 95% |  | 
 | % of residents with a Learning Disability to say they their Social Care Service helps them to have control over daily life. Source: Adult Social Care Survey (Learning Disability) | 94.2% | 88% | 81% |  | 
 | Proportion of people who use services who say those services have made them feel safe and secure. Source: Adult Social Care Survey (Learning Disability) | 93.2% | Not available | 98% |  | 

## Slide 52
OUTCOME 6: CARERS

## Slide 53: ACTION 6.2 - Emergency Care and Support
Emergency Care and Support - develop a range of appropriate, high-quality emergency care and support services that meet the needs of Carers and the cared for person.
IN PROGRESS
Year 2 Update:
Work has started to map emergency care and support services currently being used.
Year 3 Tasks:
Complete action.

## Slide 54: ACTION 6.3 - Carers Respite
Identify Carers who are delivering 35+ hours of care and support per week; and those supporting people with PMLD* who are not accessing planned respite.
NOT STARTED
Year 2 Update:
Not started.
Year 3 Tasks:
Commence work to cross-reference residents with PMLD (*Profound and Multiple Learning Disabilities) and the 50+ Carers data, to identify service needs and long-term planning

## Slide 55: ACTION 6.4 - Long-Term Planning
Long-Term Planning - identify Carers aged 50+ and work in partnership with them and the cared for person to agree the cared for person’s long-term care and support needs.
IN PROGRESS
Year 2 Update:
The Council established a Carers Resident Advisory Group in Year 1.
A Learning Disability Carers Representative joined the Learning Disability Action Plan Delivery Board.
Year 3 Tasks:
Work has started to identify those Carers aged 50+ in order to anticipate demand for services for their cared for person, particularly those who are providing care in the family home

## Slide 56: DASHBOARD - Carers
OUTCOME | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
Range of appropriate high-quality respite services in place. | No. of in-borough respite beds / units. |  |  |  |  | 
Carers aged 50+ are aware of the importance of long-term planning and engaged in communication with the cared for person and Health and Social Care. | No. of appropriate Support Plans in place for cared for people who’s Carers are aged 50+. |  |  |  |  | 
Reduction in Carer Breakdown. | No. of Hospital Admissions resulting from Carer breakdown. |  |  |  |  | 
 | No. of accommodation-based placements resulting from Carer breakdown. |  |  |  |  | 

## Slide 57: DASHBOARD - Carers
OUTCOME | INDICATOR | BASELINE | YEAR 1 | YEAR 2 | YEAR 3 | 
Proportion of residents with a Learning Disability who receive practical support (from an unpaid carer). | Yes, from someone living in my household; Yes, from someone living in another household; No Source: Adult Social Care Survey (Learning Disability) | 75.8% 25.3% 7.7% |  | 78% 27% 7% |  | 

## Slide 58: Jargon Buster
Term | Full name or meaning
ASC | Adult Social Care
ASCOF | The Adult Social Care Outcomes Framework measures outcomes and sets priorities for care and support services.
AzeusCare | AzeusCare is a digital recording system used by Newham’s Social Care Services to support delivery of services.
Barts Health NHS | Barts Health NHS Trust is a group of hospitals provide a huge range of clinical services to people in east London and beyond. Hospitals include: Newham University, St Bartholomew’s, Mile End, Royal London and Whipps Cross Hospitals.
CAMHS | Child and Adolescent Mental Health Services
C(E)TR | Care, (Education) and Treatment Reviews are for children or adults with a learning disability or autism admitted, or at risk of admission to a specialist mental health / learning disability hospital. They are CCG or NHS England leads meetings, which aim is to reduce or avoid hospital admissions though community interventions and planning. *Note a Care Education and Treatment Review is held for residents under 25 who have education needs. All others will be offered a Care and Treatment Review.
CGL Change Grow Live | Local Provider of Substance Misuse Services also known as Rise Newham.

## Slide 59: Jargon Buster
Term | Full name or meaning
CYPS | Children and Young People’s Service.
Dynamic Purchasing Vehicle | It is an electronic system for the Council to buy services. The Council sets standards that the providers/suppliers must demonstrate when they apply to join. Providers /supplier must be approved before the Council will use them.
Dynamic Support Register DSR | The DSR is a register of people with learning disabilities and/or autism who may need higher input from services and who may be at risk of being admitted to a specialist or mental health hospital. It helps local support teams to identify those who would benefit from a Care (Education) and Treatment Review. Each local borough holds a register for adults and one for children's and young people
ELFT | East London NHS Foundation Trust provides mental health, community health, and inpatient services to young people, working age adults, older adults and forensic services to Newham; it also provides a range of services outside of Newham.
Integrated Care Board ICB | NHS North East London is the Integrated Care Board (ICB) for north east London. They meet every other month to plan, discuss and make decisions about local health services and how we can best improve them for the benefit of patients and the public.
LD Forum | The Learning Disability Forum – this has been replaced by the Learning Disability Resident Advisory Group.

## Slide 60: Jargon Buster
Term | Full name or meaning
LDPAG | Learning Disability Partnership Group – this has been replaced by the Learning Disability Action Plan Delivery Board.
LDRAG Learning Disability Resident Advisory Group. | The main purpose of this group is to Advise the Learning Disability Action Plan Delivery Board and make sure that residents voices are part of the delivery of the Adult Learning Disability Action Plan.
Learning Disability Action Plan Delivery Board | The main purpose of the Delivery Board is to oversee the successful delivery of the action plan. It will monitor delivery of all of the actions within the plan to time and quality for reporting and sign off by the Learning Disability and Autism Joint Planning Group.
Learning Disability and Autism Joint Planning Group | This Group brings together statutory health and social care services, voluntary and community sector organisations, service users, and carers, to work collaboratively to test and deliver improvement and transformation initiatives.
LeDeR Learning Disabilities Mortality Review | Started in 2017 by NHS England and NHS Improvement, LeDeR is a service improvement programme that improve care, reduce care inequalities, and prevent people with a learning disability and autistic people from early deaths
NEL ICB North East London Integrated Care Board | NEL ICB is the Integrated Care Board responsible for Newham and the seven neighbouring local authorities (Barking and Dagenham, City and Hackney, Havering, Redbridge, Tower Hamlets, Waltham Forest) in North East London.

## Slide 61: Jargon Buster
Term | Full name or meaning
NHS | National Health Service
NHSE | National Health Service England
NHSE Transformation Programme | National programme to make people who have a learning disability, have autism or both healthier, and more independent
People Participation Group | ELFT People Participation within Learning Disability Services is in the process of bringing an ELFT People Participation 'group' together; the aim is working together with service users and carers to make sure people with a learning disability and/ or their carers can say what they think about the services, and how they can be improved.
Positive Behaviour Support PBS | PBS is research based model of intervention used to build understanding of the behaviour from the person’s point of view and their lifestyle, and developing an intervention based upon this interpretation. It aims to increase the quality of life and decrease ‘problem’ behaviour by teaching new skills and making changes to a person’s environment.
PMLD | This can be used to describe people who have Profound and Multiple Learning Disabilities

## Slide 62: Jargon Buster
Term | Full name or meaning
S117 / S7, S17, S37/41, S47, | These are sections in the Mental Health Act related to financial arrangement between Health and Social Care.
S75 | This is a financial arrangement between Health and Social Care for jointly funded care
SEND | Special Education Need and Disabilities
Social Prescribing | Social prescribing refers to when health professionals refer patients to non-clinical support services in the local community to help their health and wellbeing where appropriate.
STAMP | Supporting Treatment and Appropriate Medication in Paediatrics is a national programme that aims to make sure that children and families can access other treatment and support when children display behaviours that challenge (including accessing medication if they need it).
STOMP | Stopping over medication of people with learning disabilities, autism or both is a national programme aims to stop the overuse of psychotropic medications for children and young people with a learning disability, autism or both.
Well Newham | Well Newham is the Social Prescribing site to find information and support for Newham residents to look after their Health and Wellbeing.